## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After… |  |  |  | Assigned To
|  |  | Week 1 | Week 2 | Week 3 | Week 4
Cleanup | Implement session context to switch to current user | 2 | 0 |  |  |  | Matthew
Add Stock/Cleanup | Bug fix if given a space as a name and enters valid credentials it will break as it thows uncaught exception | 0.5 | 0 |  |  |  | Mark
Add Stock/Cleanup | Bug fix quantity needs upper limit | 0.5 | 0 |  |  |  | Mark
Add Stock/Cleanup | Switch date input to be datePicker in the add stock window | 1.5 | 0 |  |  |  | Kenneth
Review Stock Changes | Switch date input to be datePicker | 1.5 | 0 |  |  |  | Kenneth
Review Stock Changes | Implement date time to be able to sort stocks in review stock changes by time along with date entered | 2 | 0 |  |  |  | Kenneth
Review Stock Changes | Implement date filters in to filter by time | 2 | 0 |  |  |  | Kenneth
Add Stock | Implement a comboBox to select a type of stock is being entered | 2 | 1 | 0 |  |  | Matthew
Get Food/See Food | Implement stock types (food and munitions) for cook and officer | 3 | 1 | 0 |  |  | Matthew
Get Food/See Food | Create system to retrieve stock of a certain type | 2 | 0 |  |  |  | Matthew
See Food | Create FXML for view inventory | 1 | 0 |  |  |  | Mark
See Food/Get Food | Implement button on landing page that takes user to the view Inventory page | 0.5 | 0 |  |  |  | Kenneth
See Food | Implement functionality for a cook to see food view (a view model and methods that allows for types of stock that are food to be displayed) | 3 | 1 | 0 |  |  | Mark
See Food | Create View (codebehind) for see food (connect view model to fxml components) | 3 | 1 | 0 |  |  | Mark
Get Food | Implement the functionality for a cook to get Food aka. the Model functionality that gets called in the view model and displayed the change in the UI | 2 | 0 |  |  |  | Mark
Get Food | Log Food as it is taken out in the model and functionality to remove a stock | 2 | 1 | 0 |  |  | Kenneth
Cleanup | Add home and logout buttons for all pages | 1.5 | 0.5 | 0 |  |  | Matthew
| Estimate Totals | 30 | 5.5 | 0 | 0 | 0